## Tabelle1
WP | WP Title | Lead | Start | End | Involvement ESRs | [9 empty] | Del Rel | Del | MS | Title | Nature | Dissimination | Old Due Date | New Due Date
[5 empty] | ESR1 | ESR2 | ESR3 | ESR5 | ESR6 | ESR7 | ESR8 | ESR9 | ESR10 | ESR11
WP1 | Training Program | MOX-PoliMi | M7 | M54 | [10 empty] | D1.5 | D32 |  | Awarded PhD degrees for all ESRs | Other | Public | 2021-08-31 | 2022-02-28 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
[17 empty] | 14 | Ph.D. degrees ESRs awarded |  |  | 2021-03-01 | 2022-02-28
WP2 | Coupling Methods | BUW | M7 | M54 | [10 empty] | D2.3 | D23 |  | Reports and Software for parameterized coupling interface | Other | Confidential | 2020-07-31 | 2021-01-31 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
[17 empty] | 11 | Software for parameterized coupling interface available |  |  | 2020-08-01 | 2021-02-01
WP3 | Reduction Methods | SISSA | M7 | M54 | [10 empty] | D3.3 | D25 |  | Reports and Software for new model reduction techniques in different industrial applications and the incorporation of reduced order models in model hierarchies | Other | Confidential | 2020-08-31 | 2020-10-31 | bar: Involvement ESRs ESR1; Involvement ESRs ESR6; Involvement ESRs ESR8; Involvement ESRs ESR10
[17 empty] | 12 | Software for incorporation of reduced order models in model hierarchies available |  |  | 2020-09-01 | 2020-11-01
WP4 | Optimization Methods | FAU | M7 | M54 | [10 empty] | D4.2 | D24 |  | Reports about new techniques for the integration of model hierarchies into optimization techniques | Report | Public | 2020-07-31 | 2021-04-30 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
[15 empty] | D4.3 | D26 |  | Reports and Software for new optimization methods in different industrial applications | Other | Confidential | 2020-08-31 | 2021-04-30 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
[17 empty] | 10 | New optimization methods in different industrial applications available |  |  | 2020-05-01 | 2021-05-01
WP5 | Benchmarks for Model Hierarchies | ITMATI | M7 | M54 | [10 empty] | D5.3 | D27 |  | Benchmark cases | Report | Public | 2020-08-31 | 2021-06-30 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
[17 empty] | 13 | Benchmark cases |  |  | 2021-01-01 | 2021-07-01
[15 empty] | D5.4 | D31 |  | Reports, data and web presentation of model hierarchies for the use in training courses |  |  | 2021-08-31 | 2022-02-28
[17 empty] | 15 | Benchmarks for model hierarchies available for the use in training courses | Other | Public | 2021-03-01 | 2022-02-01
WP6 | Dissemination | JKU | M1 | M54 | [10 empty] | D6.3 | D28 |  | Final workshop on future valorisation of the results and industrial knowledge transfer | Other | Public | 2021-02-28 | 2021-09-30 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11
WP7 | Management | TUB | M1 | M54 | [10 empty] | D7.7 | D30 |  | Innovation Report | Report | Public | 2021-07-31 | 2022-01-31 | bar: Involvement ESRs ESR1 to Involvement ESRs ESR11